**ANNEX**. **FULLY COSTED EVALUATION PLAN**

The evaluations meet all the criteria for evaluation and are balanced across the portfolio and throughout the CPD period. A total of 18 evaluations are planned throughout the cycle. It includes 10 project evaluations, 1 UNSDCF MTE, 1 CPD MTE, 3 CPD outcome evaluations, 01 thematic evaluation (Gender) and 02 impact evaluations (Malaria Interventions Impact and Health Seeking Behavior). The 3 Outcome evaluations will be combined and carried-out towards the end of 2025. Evidence and learnings from these evaluations will inform program implementation to improve results, sustainability, and the design of future interventions.

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNSDCF (or equivalent)  Outcome | UNDP Strategic Plan Outcome | Evaluation Title | Partners (joint evaluation) | Evaluation commissioned by (if not UNDP) | Type of evaluation | Planned Evaluation Completion Date | Estimated Cost (USD) | Provisional Source of Funding |
| UNSCDF all outcomes | All outcomes | UNSCF midterm evaluation | UN agencies | RCO | CF evaluation | June 2025 | 40,000 | M&E Budget |
| UNDP CPD all outcomes | All outcomes | CPD midterm evaluation | Ministry of Economy, Planning and Regional Integration,  Ministry of Finance, Ministry of Foreign Affairs. | UNDP | CPD evaluation | Jun 2024 | 40,000 | M&E Budget |
| Gender Impact Evaluation |  | Gender Impact Evaluation | Ministry of Social Welfare and Women Affairs and other relevant partners | UNDP | Thematic evaluation | Oct 2023 | 35,000 | TRAC |
| By 2026, people in Guinea-Bissau enjoy improved democratic governance, peace and rule of law and their needs are met. | SP Outcome 3: Strengthen resilience to shocks and crises.  Citizen expectations for voice, development, the rule of law and accountability are met by stronger systems of democratic governance. | CPD Outcome 1 evaluation | National People’s Assembly, Ministry of Justice | UNDP | **Outcome Evaluation** | Sep 2025 | 40,000 | M&E Budget |
| Final Evaluation: Building strong institutions for sustaining peace | National People’s Assembly and Ministry of Justice | UNDP | Project Evaluation | Dec 2024 | 35,000 | Project Budget |
| Final Evaluation: Project on Support to the Electoral Cycle | CNE, GTAPE | UNDP | Project Evaluation | Dec 2025 | 35,000 | Project Budget |
| By 2026, Guinea Bissau has achieved structural economic transformation driven by enhanced productive capacity, value addition, blue economy and inclusive green growth that leaves no one behind, while capitalizing on SIDS characteristics and ensuring sustainable use and protection of natural resources. | SP Outcome 1: Advance poverty eradication in all its forms and dimensions. | CPD Outcome 2 Evaluation | Ministry of Economy, Planning and Regional Integration,  Ministry of Finance,  Ministry of Environment and Biodiversity | UNDP | **Outcome evaluation** | Sept 2025 | 40,000 | M&E Budget |
| Final evaluations: Relief and Recovery for Guinea Bissau’s MSMEs and Private Sector Response to Covid-19”. | Ministry of Economy, Planning and Regional Integration,  AIGB, | UNDP | Project Evaluation | October. 2024 | 50,000 | Project Budget |
| Mid-term evaluation: GNB 2030: Facilitating SDG Achievement in Guinea Bissau” | Prime Minister office  Vice Prime Minister office  Ministry of Economy, Planning and Regional Integration  Ministry of Finance | UNDP | Project Evaluation | May 2024 | 25,000 | Project Budget |
| Final evaluation: GNB 2030: Facilitating SDG Achievement in Guinea Bissau” | Prime Minister office  Vice Prime Minister office  Ministry of Economy, Planning and Regional Integration | UNDP | Project Evaluation | May 2026 | 40,000 | Project Budget |
| SP Outcome 2: Accelerate structural transformations for sustainable development. | Final Evaluation: Strengthen the adaptive capacity and climate resilience of Guinea-Bissau vulnerable coastal communities to climate risks | Ministry of Environment and Biodiversity | UNDP | Project Evaluation | January 2023 | 50,000 | Project Budget |
| Final Evaluation: Strengthening natural resource valuation capacities for improved planning and decision-making to conserve the global environment | Ministry of Environment and Biodiversity | UNDP | Project Evaluation | January 2022 | 30,000 | Project Budget |
| Midterm Evaluation: Strengthening climate information and early warning systems for climate resilient development and adaptation to climate change in Guinea-Bissau | National Institute for Meteorology | UNDP | Project Evaluation | September 2024 | 40,000 | Project Budget |
| Final Evaluation: Establishing a National Adaptation Planning Process in Guinea-Bissau | Ministry of Environment and Biodiversity | UNDP | Project evaluation | June 2024 | 16,000 | Project Budget |
| Midterm Evaluation: Promoting better access to modern energy services through sustainable mini-grids and low-carbon bioenergy technologies among Guinea-Bissau’s forest-dependent communities | Ministry of Natural Resources and Energy | UNDP | Project evaluation | February 2024 | 36,000 | Project Budget |
| Final Evaluation: Promoting better access to modern energy services through sustainable mini-grids and low-carbon bioenergy technologies among Guinea-Bissau’s forest-dependent communities | Ministry of Natural Resources and Enei) rgy | UNDP | Project evaluation | April 2026 | 40,000 | Project Budget |
| By 2026, the population of Guinea-Bissau, especially the most vulnerable, will have increased and equitable access and use of essential quality social services, including in emergencies. | SP Outcome 1: Advance poverty eradication in all its forms and dimensions. | CPD Outcome 3 evaluation | Ministry of Health | UNDP | **Outcome evaluation** | Sep 2025 | 40,000 | M&E budget |
| Mid-term evaluation GF:  (i) Impact of malaria control interventions in Guinea Bissau (Malaria Indicators surveys)  (ii) Enhanced health seeking behaviours to manage vulnerability and reduce risks. | 1. Bandim Health Project 2. MIS survey every 3 years | UNDP | Impact  evaluation  Impact Evaluation | Mar 2023; 2026  Jul 2023; 2026 | 920,419  167,552 | Project Budget  (2026 finding conditional on continued GF funding beyond 2021-2023) |