**ANNEX**. **FULLY-COSTED EVALUATION PLAN SURINAME 2022-2026**

The UNDP Suriname Country Office is committed to strong monitoring and evaluation processes in order to strength the quality of the programmes and projects under implementation and to ensure compliance with donor requirements. The Evaluation Plan for the programme cycle 2022 – 2026 includes all mandatory evaluations that would fall within the period and that are defined in the relevant project documents. This includes Mid-Term and Final Reviews/Evaluations. If individual projects are small in scope and with a narrow timeframe, single evaluations may not be practical and Outcome Evaluations have been proposed to cover an particular Outcome area. A Mid-Term Evaluation of the overall CPD has also been included. All the project evaluations included in this evaluation plan are for ongoing projects or projects expected to be signed early in the CPD cycle. Specific evaluations for any new projects to be signed in the new CPD cycle can be added in a yearly evaluation plan review. The evaluations identified will include a wide range of stakeholders including government, donors, partners, co-financiers and beneficiaries. Where feasible, Mid-Term Reviews/ Evaluations will be used to help to guide and steer projects that may be off-track or to accelerate progress and apply adaptive management as needed. All evaluations will include recommendations which will be recorded with management actions identified which will help to bring projects to successful completion (for Mid Term Reviews/Evaluations) and to note the achievements and to inform the design of new project and programmes (Final/Terminal Evaluations). Socioeconomic, political and environmental risks, including elections cycling, annual rainy seasons and annual holiday periods have been considered for this evaluation plan. The CO investment in quality evaluations is USD 318,000 for the period 2022-2026.

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **UNSDCF (or equivalent)**  **Outcome** | **UNDP Strategic Plan Outcome** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not UNDP)** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| MSDCF 4, 5 and 7 | Outcome 2 | CPD Mid-Term Evaluation | N/A | UNDP | Other: CPD | June 2024 | 35,000 | UNDP |
| MSDCF 4 | Outcome 2 | Social Development with emphasis on vulnerable groups (PWDs, ITPs) and implementation of the SDGs | N/A | UNDP | Outcome | October 2023 | 30,000 | UNDP |
| MSDCF 7 | Outcome 2 | Democratic Governance | N/A | UNDP | Outcome | February 2026 | 30,000 | UNDP |
| MSDCF 5 | Outcome 2 | Midterm Review GCCA+ support for Climate Change Adaptation in Suriname – Phase 2 | N/A | UNDP | Project: Midterm | March 2022 | 30,000 | Project |
| MSDCF 5 | Outcome 2 | Terminal Evaluation GCCA+ support for Climate Change Adaptation in Suriname – Phase 2 | N/A | UNDP | Project: Terminal | October 2023 | 30,000 | Project |
| MSDCF 5 | Outcome 2 | Midterm Review GEF GOLD+ in Suriname | N/A | UNDP | Project: Midterm | October 2024 | 30,000 | Project |
| MSDCF 5 | Outcome 2 | Terminal Evaluation GEF Improving Environmental Management in the Mining Sector of Suriname, with Emphasis on Artisanal and Small Scale Gold Mining (ASGM) EMSAGS | N/A | UNDP | Project: Terminal | October 2025 | 40,000 | Project |
| MSDCF 5 | Outcome 2 | Midterm Review GEF Strengthening management of protected and productive landscapes in the Surinamese Amazon | N/A | UNDP | Project: Midterm | December 2023 | 34,000 | Project |
| MSDCF 5 | Outcome 2 | Terminal Evaluation GEF Strengthening management of protected and productive landscapes in the Surinamese Amazon | N/A | UNDP | Project: Terminal | December 2026 | 34,000 | Project |
| MSDCF 4 | Outcome 2 | SDG JP Roadmap for a Sustainable Financial System for Suriname | UNEP, FAO, UNFPA | UNDP, UNEP, FAO, UNFPA | Other: Thematic | September 2022 | 20,000 | UNDP, UNEP, FAO, UNFPA |
| All MSDCF Outcomes | Outcomes 1,2,3 | Final Evaluation of Multi-Country Sustainable Development Cooperation Framework 2022-2026 | UNCT | RCO | Other: MSDCF | November 2026 | 5,000 (UNDP estimated contribution only) | UNCT |