**CPD SUDAN 2018 – 2021**

**ANNEX**. **FULLY-COSTED EVALUATION PLAN**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Costed evaluations** | **UNDP Strategic Plan Outcome** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not UNDP)** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| All outcomes  CPD (2018-2021)  Final Evaluation | Current SP (2014-2017) Outcomes  1,2,3,5&6  SDG:1,3,5,10, 11, 13&16 | CPD (2018-2021) Evaluation | UNDP and MIC, MoF | UNDP & MIC | CPD Evaluation | Oct 2020 | $80,000 | Core Budget |
| Outcome evaluation  CPD outcome 2:  By 2021, community security and stabilization of people affected by conflict is improved through utilization of effective conflict management mechanisms, peace dividends and support to peace infrastructures and durable solutions that augment peaceful coexistence and social cohesion. | SP (2014-2017)  1 & 5  SDG 1,5,13 | Outcome Evaluation | UNDP, UNEP, HCENR, MIC | GEF & UNDP | Outcome evaluation | September 2019 | $60,000 | C/S/GEF |
| Outcome evaluation  CPD outcome 3:  By 2021, people’s resilience to consequences of climate change, environmental stresses and natural hazards is enhanced through strengthened institutions, policies, plans and programmes | SP (2014-2017)  outcome 6  SDGs 1,5,16 | Outcome evaluation | UNDP, SDDRC, MIC, DRA, COR, SMOA, UNHCR, WB, FMOH, Ministry of Human Resources, Development & Labour | UNDP | Outcome evaluation | September 2019 | $60,000 | C/S |
| Adaptation to climate change  Solar for health (GCF). | SP (2014-2017)  Outcome 1 & 5  SDG 1,,5,13 | Project evaluation | UNDP, GEF, HCENR, MIC | GEF | Project terminal evaluation | May 2020 | $40,000 | GEF |
| Community Security and Stabilization Programme(C2sP) | SP (2014-2017) Outcome 6  SDG:5, 11 & 16 | Project Evaluation | SDDRC, Social Welfare, Near East Foundation, Human Security Organization, Islamic Relief, Global Health Foundation, Vet-Care Organization, Humanitarian Assistant Program and Community Management Committee | UNDP | Project final evaluation | June 2019 | $40,000 | C/S |